## Slide 1
August 14, 2018
Copyright © 2017 Deloitte Development LLC. All rights reserved.
  Oracle Cloud Implementation – HGV Test Automation

## Slide 2: Agenda
Topic
HGV Patch and Upgrade Challenges
Deloitte RPA Solution – Overview
Responsibility Matrix
HGV Test Automation Scope
Test Automation High Level Plan
Effort Summary
Cost & Estimation – Program Cost
Risk associated with Selenium Jenkins
Test Automation Exit Criteria
Assumptions
Appendix

## Slide 3: HGV - Patch and Upgrade Challenges
  Timeline and Pain Points in current test approach
Oracle Periodic Updates
HGV successfully completed a Finance and HCM/Payroll transformation on Oracle Cloud Release 12
Oracle periodically mandate quarterly updates for Cloud environments to address reported issues or to introduce new functionality.
  Business Support team performs the Patch Testing immediately post the environment is available for the critical business processes and the patch impacted functionalities.
Upgrades are typically scheduled by Oracle every 3 months. HGV plans to upgrade from R12 -> R13 on October 12, 2018.
Upgrades are 1st applied to the lower (non – production) instances and Business needs to plan the Upgrade test cycles, which includes the entire functionality and Process testing
Post the testing, Upgrade team needs to revisit the configuration/developments based on the upgrade impact analysis & the Upgrade Testing
Team spends days to execute test and analyze the patch impacted outcomes.
Individual process teams perform the test, which is not Integrated & not in sequence as per the day in Life process for HGV.
Not all test scenarios are covered for each patch testing, due to concurrent activities in Prod and Upgrade activities.
Limited availability of stakeholders / Business Users from multiple process areas to carry out testing.

## Slide 4
Runtime Notification
Summary reports via emails with error step screenshot of failed test steps
Web based dashboards
For remote monitoring and execution of scripts with visibility to historical data
Powered by best of breed test automation tools
Selenium, Jenkins and Automation
Anywhere and UIPath
One Stop Shop for End to end functional testing automation
For Oracle Cloud standard test cases
Intuitive to use
Enriched and simplified user interface provide modern experience for test script, data and execution management
Plug and play
Installation, enhancement and upgrades supported by Deloitte team and alignment with oracle ERP/HCM cloud releases/updates
Deloitte RPA Test Automation Solution
Deloitte RPA Solution - Overview
Deloitte RPA solution provides a significant opportunity for reduction in the testing efforts required for functional testing (unit, regression, performance etc.) during ERP/HCM cloud implementations and regression testing needed during frequent patching and application upgrades.

## Slide 5
Responsibility Matrix
HGV and Deloitte have primary or secondary responsibility for the deliverables identified below
ACTIVITY/ DELIVERABLE | DESCRIPTION | RESPONSIBILITY |  | 
 |  | DELOITTE AMS | DELOITTE RPA | HGV
Release Notes Assessment Sheet | Review Quarterly Patch Release Notes | Primary | N.A. | Secondary
Release Readiness Plan | Test scripts to be completed along with the resource assignments and the test duration. Any new features to be tested will be included in the plan | Primary | N.A | Secondary
Release Execution Plan | Describes the execution plan for test scripts and any retrofitting based on the system changes. Document any SR fixes. | Primary | N.A | Secondary
Defect Tracker | Document, address and fix defects that may arise post patch application | Primary | N.A | Secondary
Data Preparation | Provide test data for the regression test scenarios | Primary | N.A | Secondary
Test Execution | Execute Manual and Automated test scripts in test instance | Combined |  | Secondary
Automation Script | Creation and Updating of automation scripts within the specified scope | N.A | Primary | N.A
Review and validate results | Validate test results to ensure it has not broken anything | Secondary |  | Primary
Release Cutover Plan | Document steps to roll out release to production | Primary |  | Secondary
Release Test Exit Criteria Plan | Measure and evaluate release test exit results | Secondary |  | Primary
Release Testing Production Plan | Plan production downtime associated with the feature release and communications. Release production environment to business users | Secondary |  | Primary

## Slide 6
We compared the existing test scripts that are used in HGV and evaluated the development that is needed. Deloitte is willing to work with HGV to identify the “Business Critical Scenarios” that you would like to automate for future release cycles
Module Scope | High Priority (44%) | Medium Priority (35%) | Low Priority(21%) | Total Scripts
Absence | 7 | 17 | 4 | 28
AP | 30 | 14 | 15 | 59
AR | 3 | 3 | 1 | 7
CM | 1 | 5 | 0 | 6
Core HR | 28 | 12 | 19 | 59
FA | 2 | 5 | 3 | 10
GL | 21 | 17 | 11 | 49
Payroll | 49 | 50 | 22 | 121
PPM | 5 | 5 | 1 | 11
Procurement | 19 | 14 | 6 | 39
Taleo | 8 | 0 | 0 | 8
Grand Total | 173 | 138 | 82 | 397
Test Automation Scope at HGV
Include ERP and HCM scope including interfaces.

## Slide 7: UIPATH FULL AUTOMATION

## Slide 8: Effort Summary and Cost
Calculation
Total Scripts = 397
RPA Technical & Testing Effort= 5,896 Hrs.
Total Efforts : 5,896 Hrs.
 | Simple |  | Medium |  | Complex | 
Type | No. of Scripts | Efforts/script | No. of Scripts | Efforts/script | No. of Scripts | Efforts/script
New | 204 | 12 | 84 | 23 | 20 | 46
Retrofit | 38 | 4 | 42 | 8 | 9 | 12
UIPath
Notes: Standard scripts that are part of automation will have estimation based on FTE
  How many FTE (Tech as well as Func) we will need to manage and execute the scripts based on timeline we proposed
  What phase will it cover
Custom scripts details
  What will be manual vs. automated
  Estimation model for automating it based on complexity
  Resource requirement

## Slide 9: Test Automation High Level Plan - UiPath
Review Deloitte Test Repository
Identify test scripts to be re-factored and newly developed
Prepare the plan to automate the test scripts
Sep
2018
R13 Upgrade
Future Release Upgrades
R13.x1 Upgrade
R13.x2 Upgrade
Oct
2018
Dec
2018
Mar
2019
200 Hours
Conduct Regular Release Management activities leveraging automated and manual test scripts as part of the release management plan
990 Hours
Conduct Regular Release Management activities leveraging automated and manual test scripts as part of the release management plan
990 Hours
Conduct Regular Release Management activities leveraging automated and manual test scripts as part of the release management plan
990 Hours
Automate initial 30% test scripts by priority chart
Gather associated test data
Conduct Unit/Functional Test
2000 Hours
Automate remaining 70% test scripts by priority chart
Gather associated test data
Conduct Unit/Functional Test
3896 Hours
Estimated effort of 990 hours includes:
Update/addition of ~70 incremental automation scripts during each release cycle
New Scripts above and beyond 70 will be analyzed in current Release and will be delivered in Release +1
Test data creation as needed by the Automation Bots
Execution/Remediation of Automation Bots

## Slide 10: UIPath Cost
Scope | Total Hrs. | Client Fees Billed | Total Scripts | Automation Type
Process Area Absence AP AR CM Core HR FA GL Payroll PPM Procurement Taleo | Approx. 5,896 | Approx. $298,003 | 389 | Full Automation with UI Path Licensing Cost (One time cost) Breakdown (include Onsite tech lead for 8 weeks) Effort = $265,003/- + UIPath Licensing = $33,000/-
 | Approx. 990 per quarter release (x4)* | Approx. $162,240 for an year | 70 scripts per Upgrade | Incremental Automation over an year with UI Path Licensing Cost Effort = $129,240/- + UIPath Licensing = $33,000/-
Yearly Licensing Cost (UiPath)
Software Cost (attended) 7 X Studio – $21,000 Bots 10 X Bots – $12,000 ($1,200 per bot)
*Break down of 3960 hours: 990 hours for each release upgrade (x4) Split
Automation Bots Execution for testing (fixed for each upgrade) – 90 hours
Update/addition of ~70 incremental automation for each release upgrade – 900 hours
Notes: Standard scripts that are part of automation will have estimation based on FTE
  How many FTE (Tech as well as Func) we will need to manage and execute the scripts based on timeline we proposed
  What phase will it cover
Custom scripts details
  What will be manual vs. automated
  Estimation model for automating it based on complexity
  Resource requirement

## Slide 11: SELENIUM-JENKINS – AUTOMATION

## Slide 12: Effort Summary
Calculation
Total Scripts = 397
RPA Technical & Testing Effort= 12,018
Total Efforts : 12,018 Hrs.
 | Simple |  | Medium |  | Complex | 
Type | No. of Scripts | Efforts/script | No. of Scripts | Efforts/script | No. of Scripts | Efforts/script
New | 216 | 27 | 130 | 36 | 26 | 45
Retrofit | 10 | 8 | 13 | 16 | 2 | 24
Selenium
Notes: Standard scripts that are part of automation will have estimation based on FTE
  How many FTE (Tech as well as Func) we will need to manage and execute the scripts based on timeline we proposed
  What phase will it cover
Custom scripts details
  What will be manual vs. automated
  Estimation model for automating it based on complexity
  Resource requirement

## Slide 13: Test Automation High Level Plan – Selenium Jenkins
Review Deloitte Test Repository
Identify test scripts to be re-factored and newly developed
Prepare the plan to automate the test scripts
Sep
2018
R13 Upgrade
Future Release Upgrades
R13.x1 Upgrade
R13.x2 Upgrade
Oct
2018
Dec
2018
Mar
2019
200 Hours
Conduct Regular Release Management activities leveraging automated and manual test scripts as part of the release management plan
990 Hours
Conduct Regular Release Management activities leveraging automated and manual test scripts as part of the release management plan
990 Hours
Conduct Regular Release Management activities leveraging automated and manual test scripts as part of the release management plan
990 Hours
Automate initial 10% test scripts by priority chart
Gather associated test data
Conduct Unit/Functional Test
1200 Hours
Automate 25% test scripts by priority chart
Gather associated test data
Conduct Unit/Functional Test
2806 Hours
Estimated effort of 990 hours includes:
Update/addition of ~35 incremental automation scripts during each release cycle
New Scripts above and beyond 35 will be analyzed in current Release and will be delivered in Release +1
Test data creation as needed by the Automation Bots
Execution/Remediation of Automation Bots
Automate 35% test scripts by priority chart
Gather associated test data
Conduct Unit/Functional Test
4006 Hours
Automate remaining 30% test scripts
Gather associated test data
Conduct Unit/Functional Test
4006 Hours
Jun
2019

## Slide 14: Cost & Estimation : Program Cost
#Break down of 3960 hours: 990 hours for each release upgrade (x4) Split
Automation Bots Execution for testing (fixed for each upgrade) – 90 hours
Update/addition of ~35 incremental automation for each release upgrade – 900 hours
Scope | Total Hrs. | Client Fees Billed | Total Scripts | Automation Type
Process Area Absence AP AR CM Core HR FA GL Payroll PPM Procurement Taleo | Approx. 12,018 | Approx. $486,763 | 389 | Full Automation with (One time cost) – include onsite tech lead role for 8 weeks
 | Approx. 990* per quarter release (x4) | Approx. $129,240/- | 35 scripts per Upgrade | Incremental Automation over an year
Yearly Licensing Cost
No Licensing Cost
Selenium
Notes: Standard scripts that are part of automation will have estimation based on FTE
  How many FTE (Tech as well as Func) we will need to manage and execute the scripts based on timeline we proposed
  What phase will it cover
Custom scripts details
  What will be manual vs. automated
  Estimation model for automating it based on complexity
  Resource requirement

## Slide 15: SELENIUM-JENKINS – 40% Script with KT

## Slide 16: Effort Summary
Calculation
Total Scripts = 397
RPA Technical & Testing Effort= 12,018
Total Efforts of 40% script: 4,815 Hrs.
 | Simple |  | Medium |  | Complex | 
Type | No. of Scripts | Efforts/script | No. of Scripts | Efforts/script | No. of Scripts | Efforts/script
New | 216 | 27 | 130 | 36 | 26 | 45
Retrofit | 10 | 8 | 13 | 16 | 2 | 24
Selenium
Notes: Standard scripts that are part of automation will have estimation based on FTE
  How many FTE (Tech as well as Func) we will need to manage and execute the scripts based on timeline we proposed
  What phase will it cover
Custom scripts details
  What will be manual vs. automated
  Estimation model for automating it based on complexity
  Resource requirement

## Slide 17: Test Automation High Level Plan – Selenium Jenkins
Review Deloitte Test Repository
Identify test scripts to be re-factored and newly developed
Prepare the plan to automate the test scripts
Sep
2018
R13 Upgrade
Future Release Upgrades
R13.x1 Upgrade
R13.x2 Upgrade
Oct
2018
Dec
2018
200 Hours
Automate initial 10% test scripts by priority chart
Gather associated test data
Conduct Unit/Functional Test
1200 Hours
Automate 30% test scripts by priority chart
Gather associated test data
Conduct Unit/Functional Test
Perform KT
3615 Hours
HGV IT TEAM will create 60% scripts and maintain going forward

## Slide 18: Cost & Estimation : Program Cost
Scope | Total Hrs. | Client Fees Billed | Total Scripts | Automation Type
Process Area Absence AP AR CM Core HR FA GL Payroll PPM Procurement Taleo | Approx. 4,815 | Approx. $235,492 | 156 | Full Automation with (One time cost) – include onsite tech lead role for 8 weeks $ Effort = 215,492 + Selenium Deloitte Framework - $20,000
Yearly Licensing Cost
No Licensing Cost
Selenium
Notes: Standard scripts that are part of automation will have estimation based on FTE
  How many FTE (Tech as well as Func) we will need to manage and execute the scripts based on timeline we proposed
  What phase will it cover
Custom scripts details
  What will be manual vs. automated
  Estimation model for automating it based on complexity
  Resource requirement

## Slide 19: Risk associated with Selenium Jenkins
Supports limited unattended Automation
Efforts required to customize existing test scripts is higher compared to UiPath
Requires competency in JAVA to develop new test scripts either external or internal to HGV
Being Open source product, dedicated support is not available as a result future releases can have bugs and new features which will require learning of the new toolset.

## Slide 20
Exit Criteria
Exceptions to any of the above must be signed off by Leadership/PMO
All available integration with Boundary systems tested
90% pass rate for executed automated test scripts
End to End transaction testing is successful that includes integrations
Automation bot test execution outcomes and associated impacts are shared with client stakeholders for review and final approval

## Slide 21
Assumptions
Deloitte AMS team and Automation team review patch/release upgrade documents, assesses impacted modules and processes
Deloitte Automation team support shares automation execution plan for the impacted scripts with client’s IT/Business leads
Plan is reviewed, modified as applicable and approved by client
Post approval from client, Automation bots will execute testing scripts in patched/ upgraded testing environments as per plan
Post analysis, any changes required to existing configurations are performed and testing is re-executed
For scripts that require enhancements as a result of UX/Patch impact are updated by automation support team within specified script scope
Scripts fine tuned and enhanced are approved by client and tested in the patched / upgraded testing environments
Automation team will not be testing changes applied to security roles and duties
990 hours for each release upgrade is split across execution of bots and creation/updating of ~70 scripts for UiPath and ~35 scripts for Selenium. The hours for each of the release upgrade will not carry forward to the next quarter release for an year.
Additional scripts over and above 70 for UiPath and 35 for Selenium Jenkins will be charged as part of separate change order
New Scripts will be analyzed in current Release and will be delivered in Release +1

## Slide 22: Appendix

## Slide 23
HGV Script Automation Effort Estimation - UIPATH
HGV Module Scope | Total Scripts in HGV | Automated scripts in Deloitte Repository | Total Scripts to be newly developed |  |  | Total Scripts to be refactored |  |  | Effort Estimate for New Development |  |  | Effort Estimate for scripts to be refactored |  | 
 |  |  | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex
Absence | 28 | 5 | 23 | 0 | 0 | 3 | 1 | 1 | 276 | 0 | 0 | 12 | 8 | 12
AP | 59 | 17 | 28 | 10 | 4 | 9 | 6 | 2 | 336 | 230 | 184 | 36 | 48 | 24
AR | 7 | 6 | 0 | 1 | 0 | 1 | 3 | 2 | 0 | 23 | 0 | 4 | 24 | 24
CM | 6 | 6 | 47 | 1 | 0 | 5 | 1 |  | 564 | 23 | 0 | 0 | 0 | 0
Core HR | 59 | 11 | 0 | 9 | 1 | 4 | 6 | 1 | 0 | 207 | 46 | 20 | 8 | 0
FA | 10 | 0 | 22 | 3 | 4 | 0 | 0 | 0 | 264 | 69 | 184 | 16 | 48 | 12
GL | 49 | 20 | 79 | 35 | 2 | 13 | 7 |  | 948 | 805 | 92 | 52 | 56 | 0
Payroll | 121 | 5 | 2 | 6 | 3 |  | 4 | 1 | 24 | 138 | 138 | 0 | 32 | 12
PPM | 11 | 11 | 3 | 19 | 6 | 2 | 8 | 1 | 36 | 437 | 276 | 0 | 0 | 0
Procurement | 39 | 8 | 23 | 0 | 0 | 1 | 6 | 1 | 276 | 0 | 0 | 8 | 64 | 12
Taleo | 8 | 20 | 0 | 0 | 0 | 13 | 7 |  | 336 | 230 | 184 | 4 | 48 | 12
 | 397 | 89 | 204 | 84 | 20 | 38 | 42 | 9 | 2448 | 1932 | 920 | 152 | 336 | 108
 |  |  |  |  | 308 |  |  | 89 |  |  | 5300 |  |  | 596
Grand Total | 5,896
Given below is the effort estimates for new development and refactoring of automated test scripts based on the test script scope at HGV
UiPATH

## Slide 24
UiPath Test Automation – Resource Plan (For Internal Reference)
* Estimated scope: ~320 Test scripts
This is one time cost for automating 397 scripts. These include ERP and HCM.
Full Automation (~390 Test scripts) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deloitte |  |  |  |  | Assess | Confirm and Build |  |  |  | Test & Deliver |  | Confirm and Build |  |  | Test & Deliver |  |  | 
Role | Level | Role | Location | Rate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Total Hrs. | Total $
TECH | Manager | Developer | PMO | $ 161.12 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 360 | $ 58,003.20
TECH | Sr. Consultant | Developer | Offshore | $ 38.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 20,520.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 495 | $ 15,840.00
USI ERP | Consultant | Functional | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
USI Absence | Consultant | Functional | Offshore | $ 46.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 24,840.00
USI Payroll | Consultant | Functional | Offshore | $ 46.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 24,840.00
Total |  |  |  |  | 450 | 495 | 495 | 495 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 540 | 6255 | $265,003.20

## Slide 25
HGV Module Scope | Total Scripts in HGV | Automated scripts in Deloitte Repository | Total Scripts to be newly developed |  |  | Total Scripts to be refactored |  |  | Effort Estimate for New Development |  |  | Effort Estimate for scripts to be refactored |  | 
 |  |  | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex
Absence | 28 | 0 | 26 | 1 | 1 | 0 | 0 | 0 | 702 | 36 | 45 | 0 | 0 | 0
AP | 59 | 8 | 20 | 25 | 6 | 4 | 4 | 0 | 540 | 900 | 270 | 32 | 64 | 0
AR | 7 | 3 | 1 | 2 | 1 | 0 | 2 | 1 | 27 | 72 | 45 | 0 | 32 | 24
CM | 6 | 4 | 2 | 0 | 0 | 3 | 1 | 0 | 54 | 0 | 0 | 24 | 16 | 0
Core HR | 59 | 0 | 51 | 7 | 1 | 0 | 0 | 0 | 1377 | 252 | 45 | 0 | 0 | 0
FA | 10 | 0 | 0 | 9 | 1 | 0 | 0 | 0 | 0 | 324 | 45 | 0 | 0 | 0
GL | 49 | 3 | 34 | 8 | 4 | 1 | 2 | 0 | 918 | 288 | 180 | 8 | 32 | 0
Payroll | 121 | 0 | 79 | 39 | 3 | 0 | 0 | 0 | 2133 | 1404 | 135 | 0 | 0 | 0
PPM | 11 | 0 | 0 | 8 | 3 | 0 | 0 | 0 | 0 | 288 | 135 | 0 | 0 | 0
Procurement | 39 | 7 | 2 | 25 | 5 | 2 | 4 | 1 | 54 | 900 | 225 | 16 | 64 | 24
Taleo | 8 | 0 | 1 | 6 | 1 | 0 | 0 | 0 | 27 | 216 | 45 | 0 | 0 | 0
 | 397 | 25 | 216 | 130 | 26 | 10 | 13 | 2 | 5832 | 4680 | 1170 | 80 | 208 | 48
 |  |  |  |  | 372 |  |  | 25 |  |  | 11682 |  |  | 336
SELENIUM
HGV Script Automation Effort Estimation - SELENIUM
Given below is the effort estimates for new development and refactoring of automated test scripts based on the test script scope at HGV
Grand Total | 12,018

## Slide 26
Selenium Full Automation – Resource Plan (Internal reference
* Estimated scope: ~320 Test scripts
Full Automation (4006 hours) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deloitte |  |  |  |  | Confirm and Build |  |  |  |  |  |  |  | Test and Deliver |  |  |  |  | 
Role | Level | Role | Location | Rate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Total Hrs. | Total $
TECH | Manager | PMO | Offshore | $ 161.12 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 360 | $ 58,003.20
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
USI ERP | Consultant | Functional | Offshore | $ 32.00 | 0 | 0 | 45 | 45 | 45 | 45 | 0 | 45 | 45 | 45 | 45 | 45 | 405 | $ 12,960.00
USI Payroll | Consultant | Functional | Offshore | $ 46.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 24,840.00
USI Core HR | Consultant | Functional | Offshore | $ 46.00 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 360 | $ 16,560.00
Total |  |  |  |  | 270 | 270 | 315 | 315 | 405 | 405 | 360 | 405 | 405 | 405 | 405 | 405 | 4365 | $ 198,763.20
Full Automation (4006 hours) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deloitte |  |  |  |  | Confirm and Build |  |  |  |  |  |  |  | Test and Deliver |  |  |  |  | 
Role | Level | Role | Location | Rate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Total Hrs. | Total $
TECH | Sr. Consultant | Developer | Offshore | $ 38.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 20,520.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 180 | $ 5,760.00
USI ERP | Consultant | Functional | Offshore | $ 32.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 225 | $ 7,200.00
USI Payroll | Consultant | Functional | Offshore | $ 46.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 24,840.00
USI Core HR | Consultant | Functional | Offshore | $ 46.00 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 360 | $ 16,560.00
Total |  |  |  |  | 225 | 225 | 225 | 225 | 270 | 270 | 270 | 315 | 360 | 360 | 360 | 360 | 4005 | $ 144,000.00
Full Automation (4006 hours) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deloitte |  |  |  |  | Confirm and Build |  |  |  |  |  |  |  | Test and Deliver |  |  |  |  | 
Role | Level | Role | Location | Rate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Total Hrs. | Total $
TECH | Sr. Consultant | Developer | Offshore | $ 38.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 20,520.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 180 | $ 5,760.00
USI ERP | Consultant | Functional | Offshore | $ 32.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 225 | $ 7,200.00
USI Payroll | Consultant | Functional | Offshore | $ 46.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 24,840.00
USI Core HR | Consultant | Functional | Offshore | $ 46.00 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 360 | $ 16,560.00
Total |  |  |  |  | 225 | 225 | 225 | 225 | 270 | 270 | 270 | 315 | 360 | 360 | 360 | 360 | 4005 | $ 144,000.00

## Slide 27
Selenium 40% Automation with KT– Resource Plan (Internal reference
* Estimated scope: ~320 Test scripts
40% Automation scripts with KT Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Deloitte |  |  |  |  | Assess | Confirm and Build |  |  |  | Test & Deliver |  | Confirm and Build |  |  | Test & Deliver |  |  | 
Role | Level | Role | Location | Rate | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Total Hrs. | Total $
TECH | Manager | Developer | PMO | $ 161.12 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 270 | $ 43,502.40
TECH | Sr. Consultant | Developer | Offshore | $ 38.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 20,520.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 17,280.00
USI ERP | Consultant | Functional | Offshore | $ 32.00 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 450 | $ 14,400.00
USI Absence | Consultant | Functional | Offshore | $ 46.00 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 540 | $ 24,840.00
USI Payroll | Consultant | Functional | Offshore | $ 46.00 | 0 | 0 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 450 | $ 20,700.00
TECH | Sr. Consultant | KT | Offshore | $ 38.00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 45 | 45 | 135 | $ 5,130.00
Total |  |  |  |  | 315 | 315 | 405 | 405 | 405 | 405 | 450 | 450 | 450 | 450 | 450 | 450 | 5085 | $ 215,492.40

## Slide 28: Release Management Effort Estimate for Quarter releases (Internal)
Release Management with Selenium Jenkins (~70 scripts per Quarter release) |  |  |  |  |  |  |  |  |  | 
Deloitte |  |  |  |  | Assess |  | Confirm and Build |  |  | 
Role | Level | Role | Location | Rate | Week 1 | Week 2 | Week 3 | Week 4 | Total Hrs. | Total $
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 180 | $ 5,760.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 180 | $ 5,760.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 180 | $ 5,760.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 180 | $ 5,760.00
TECH | Consultant | Developer | Offshore | $ 32.00 | 45 | 45 | 45 | 45 | 180 | $ 5,760.00
USI ERP | Consultant | Functional | Offshore | $ 32.00 | 0 | 0 | 0 | 45 | 45 | $ 1,440.00
USI HCM | Consultant | Functional | Offshore | $ 46.00 | 0 | 0 | 0 | 45 | 45 | $ 2,070.00
Total |  |  |  |  | 225 | 225 | 225 | 315 | 990 | $32,310.00
Resource effort $ value for supporting bots over 4 upgrades for an year will be $32,310 * 4 = $129,240/-
In case of a UI Path the licensing cost per year will be extra.

## Slide 29: HGV E2E Scenarios List
Scenario ID | Test Case | Track | Module
E2E-003-01 | Invoice to Payment - Vision Wireless – HGV | ERP | AP
E2E-004 | Invoice to Payment - CLD HGV | ERP | AP
E2E-005-01 | Invoice to Payment - Concur AMEX Expenses HGV | ERP | AP
E2E-005-02 | Invoice to Payment - Concur PCard Expenses HGV | ERP | AP
E2E-006-01-01 | Invoice to Payment - Concur Manual Expenses HGV | ERP | AP
E2E-009-01 | Invoice to Payment - Voice - HGV +HOA | ERP | AP
E2E-022 | Payables period close | ERP | AP
E2E-053-02 | Manual Check Request HOA Operations | ERP | AP
E2E-054-01 | Invoice to Payment - Scanned Invoice HOA - Escrow | ERP | AP
E2E-050 | Invoice to Payment - Scanned Invoice HGV - Non PO | ERP | AP
E2E-007 | Invoice to Cash - Kyriba Receipts Internal Receivables (HOA/FFS) | ERP | AR
E2E-008 | Invoice to Cash - Manual Receipts - Externals Receivables | ERP | AR
E2E-016 | Import GL Journals from Chorus HGV | ERP | GL
E2E-016-01 | Import GL Journals from Harland HGV | ERP | GL
E2E-016-02 | Import Journals from Kyriba HGV | ERP | GL
E2E-016-03 | Import Journals from Kyriba HOA | ERP | GL
E2E-016-04 | Import Journals from Kyriba FFS | ERP | GL
E2E-036 | Import GL Journals from Chorus - HOA | ERP | GL
E2E-037 | Import GL Journals from VOICE - HOA | ERP | GL
E2E-051-01 | Voice to GL - Payables to Payment HOA Reserve | ERP | GL
E2E-052-01 | Voice to GL - Payables to Payment HOA Operations | ERP | GL
E2E-055 | Payroll to GL Testing for HGV Employees | HCM | Payroll
E2E-056-01 | Payroll to GL Testing for HOA Employees | HCM | Payroll
E2E-057 | Payroll to GL Testing for FFS Employees | HCM | Payroll
E2E-058-01 | Payroll Elements Testing to GL - Earnings, Deduction, etc. | HCM | Payroll
E2E-059 | PTO Accrual - HGV | HCM | Payroll
E2E-060 | Wages Accrual - HGV | HCM | Payroll
E2E-061 | PTO Accrual - HOA | HCM | Payroll
E2E-062 | Wages Accrual - HOA | HCM | Payroll
E2E-063 | PTO Accrual - FFS | HCM | Payroll
E2E-064 | Wages Accrual FFS | HCM | Payroll
E2E-065-01 | Import Journals from FuseBox(Shift4) - Chorus | ERP | GL
E2E-066 | Import Journals from CCT - Chorus | ERP | GL
E2E-013 | Fixed Asset projects - Project Costing to Capitalization | ERP | PPM
E2E-011 | IT Projects - Project Costing to Capitalization - Non-PO | ERP | PPM
E2E-012 | Construction Projects - Project Costing to Inventory | ERP | PPM
E2E-001 | Requisition to Payment - Scanned Invoice HGV - PO | ERP | Procurement
E2E-002 | Requisition to Payment - Asset - HGV | ERP | Procurement
E2E-014-01-01 | Purchase Order to Payment - BirchStreet - HGV | ERP | Procurement
E2E-014-02 | Purchase Order to Payment - BirchStreet - HOA | ERP | Procurement
E2E-034-01 | Requisition to Payment - Scanned Invoice HOA - Operations | ERP | Procurement

## Slide 30: Automation Estimation Model between Selenium and UiPath
Process Criteria | Simple | Medium | High
Number of Screens | 3-4 | 6-10 | 8-15
Steps | 5-10 without alternate flow | 10-20 Incl. alternate flows | 20-40 Incl. nested rules
Input Data | Digital, Structured & Standardized | Digital, Structured & Standardized | Digital, Structured & Standardized
# of Business Rules | 5-10 | 10-20 | 20-30
Data Handling | Copy/paste | Copy, paste, read and modify data | Copy, paste, read data, data enrichment
Operational Risk Level | Non-core processing (Test environments) | Time or business dependent processing | Business critical BAU processing
Typical Functional/Business Analyst Effort | 3 Hrs | 5 Hrs | 10 Hrs
Typical Developer Effort (Retrofit) | 3 Hrs. | 7 Hrs. | 10 Hrs.
Typical Build Duration (New) – Selenium | 30 Hrs | 41 Hrs | 55 Hrs
Typical Developer Effort (New) – Selenium | 27 Hrs. | 36 Hrs. | 45 Hrs.
Typical Developer Effort (New) – UIPath | 9 Hrs | 18 Hrs | 36 Hrs.
Typical Build Duration (New) - UIPath | 12 Hrs | 23 Hrs | 46 Hrs

## Slide 31
We compared the existing test scripts that are used in HGV and evaluated the development that is needed. Deloitte is willing to work with HGV to identify the “Business Critical Scenarios” that you would like to automate for future release cycles
Module Scope | Low | Medium | High | Total Scripts
Absence | 26 | 1 | 1 | 28
AP | 24 | 29 | 6 | 59
AR | 1 | 4 | 2 | 7
CM | 5 | 1 |  | 6
Core HR | 51 | 7 | 1 | 59
FA |  | 9 | 1 | 10
GL | 35 | 10 | 4 | 49
Payroll | 79 | 39 | 3 | 121
PPM |  | 8 | 3 | 11
Procurement | 4 | 29 | 6 | 39
Taleo | 1 | 6 | 1 | 8
Grand Total | 226 | 143 | 28 | 397
HGV Test Automation Scope by Complexity
Include ERP and HCM scope.

## Slide 32: Thank You !!!